RISE Viera and RISE Glen Kernan Park | April-June 2026

Training Objective

The training roadmap is built around Priority 1: fix lead intake and first-response reliability across both communities. The course is designed to improve speed-to-lead, discovery quality, follow-up discipline, and closing consistency while maintaining required response benchmarks and closing ratios.

Training Schedule

RISE Viera

•	Initial in-person training: 04/15/26

•	In-person follow-up with Morgan Matlock: 05/13/26

•	Weekly virtual follow-up calls begin the week of 04/20/26

•	Corporate support continues between follow-up calls

RISE Glen Kernan Park

•	Initial in-person training: Thursday 04/23/26

•	In-person follow-up with Morgan Matlock: Thursday 05/21/26

•	Weekly virtual follow-up calls begin the week of 04/27/26

•	Corporate support continues between follow-up calls

Training Course Summary

•	Lead intake workflow and first-response reliability standards

•	Lead contact expectations across calls, texts, & email follow-up

•	Discovery questions, needs analysis, and next-step control

•	Tour execution, objection handling, and closing discipline

•	Follow-up quality review through call sentiment, coaching, & accountability

30 / 60 / 90 Day Roadmap

30 Days

Complete in-person training at each community. Audit current lead intake and first-response practices, reinforce discovery and tour execution, and standardize follow-up expectations to support stronger closing consistency.

31-60 Days

Conduct May in-person follow-up visits with Morgan Matlock. Review response times, lead contact completion, tour conversion, and closing performance; coach teams on gaps immediately when benchmarks are not being met.

61-90 Days

Continue virtual follow-up calls and corporate support. Morgan will monitor follow-up execution and lead contacts, review call sentiments, and provide weekly coaching whenever required benchmarks or closing ratios fall below expectations.

Ongoing Accountability

•	Morgan Matlock will monitor lead follow-up activity and contact cadence to ensure timely responses.

•	Call sentiment reviews will be used to identify coaching opportunities and reinforce closing best practices.

•	Weekly coaching will be provided when teams are not meeting required benchmarks.

•	Corporate support will remain engaged to reinforce execution, reporting, and issue escalation.